## consolidated
User Story 1	time estimate
a frontend to place the app	3h
OAuth to spotify	2.5h
store the token	2h
test api for spotify	2.5h
test api for imdb	2.5h
get user playlist genre	0.5h
query imdb with the genres	0.5h
algorithm to sort the movies	1h
database to store user and their movie list	3h
option to remove movie form list	1h
excluded movie list in database	1h

## Fanjie Gao
User Story 1	time estimate
a frontend to place the app	3h
OAuth to spotify	2h
store the token	1h
test api for spotify	3h
test api for imdb	3h
get user playlist genre	0.1h
query imdb with the genres	0.1h
algorithm to sort the movies	0.5h
database to store user and their movie list	3h
option to remove movie form list	1h
excluded movie list in database	1h

## Ruoxuan Li
user sotry 1			time estimation
a frontend to place the app			3h
OAuth to spotify			3h
store the token			3h
test api for spotify			2h
test api for imdb			2h
get user playlist genre			1h
query imdb with the genres			1h
algorithm to sort the movies			2h
database to store user and their movie list			3h
option to remove movie form list			1h
excluded movie list in database			1h