## consolidated
User Story 1 | time estimate
a frontend to place the app | 3h
OAuth to spotify | 2.5h
store the token | 2h
test api for spotify | 2.5h
test api for imdb | 2.5h
get user playlist genre | 0.5h
query imdb with the genres | 0.5h
algorithm to sort the movies | 1h
database to store user and their movie list | 3h
option to remove movie form list | 1h
excluded movie list in database | 1h

## Fanjie Gao
User Story 1 | time estimate
a frontend to place the app | 3h
OAuth to spotify | 2h
store the token | 1h
test api for spotify | 3h
test api for imdb | 3h
get user playlist genre | 0.1h
query imdb with the genres | 0.1h
algorithm to sort the movies | 0.5h
database to store user and their movie list | 3h
option to remove movie form list | 1h
excluded movie list in database | 1h

## Ruoxuan Li
user sotry 1 | time estimation
a frontend to place the app | 3h
OAuth to spotify | 3h
store the token | 3h
test api for spotify | 2h
test api for imdb | 2h
get user playlist genre | 1h
query imdb with the genres | 1h
algorithm to sort the movies | 2h
database to store user and their movie list | 3h
option to remove movie form list | 1h
excluded movie list in database | 1h